## GIS Roadmap
Last updated | 2013-04-03
[6 empty] | FY14 Q1 | [5 empty] | FY14 Q2 | [5 empty] | FY14 Q3 |  |  | FY14 Q4
[6 empty] | Feb |  | Mar |  | Apr |  | May |  | Jun |  | Jul |  | Aug | Sept | Oct | Nov | Dec | Jan
Iteration # | [5 empty] | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43-44 | 45 |  |  |  |  | Product Owner | [6 empty] | Engineering Team
| Work Area | EPIC | JIRA | Key Activities | Comments | [19 empty] | US | RL | JP | LS | SS | GI | NS | DS | SS | SM | SJ | SK | VR | VK | PS
| Inventory | [22 empty] | SA
|  | Set up environments for GIS (Inventory Management) | PGGISIMS-3 | Environment setup with Talend installation | bar: RL
|  | Data Ingestion in Hadoop | PGGISIMS-10 | Data Ingestion in Hadoop framework and implementation | bar: US to JP
Inventory Reporting
| Order | [22 empty] | SA
|  | (ASDA)-Caputure requirements for ASDA | PGGISOM-9 | Technical and functional requirements for ASDA | bar: RL
|  | (ASDA)-Set up environments for GIS for Order Management | PGGISOM-2 | Environment setup with Talend installation | bar: RL
|  | Data Ingestion in Hadoop | PGGISOM-12 | Data Ingestion in Hadoop framework and implementation | bar: US to JP
ASDA Phase 2
| CS and CA | [22 empty] | SA
|  | (CA)-Customer Account Track | PGGISCS-1 | LDM, PDM, Source/Target mapping, Design and Development and Testing of Customer Domain | bar: JP
|  | (US)-CS Data Feeds | PGGISCS-6 | Datafeed requirements and ISD datafeed delivery | bar: JP
CS Reporting Phase 1
CS Reporting Phase 2
| Vista | [22 empty] | IS
|  | Outbound Phase 1 |  | Outbound Phase 1 | bar: VR to PS
|  | Outbound Phase 2 | PGGISVISTA-34 | Outbound Phase 2 | bar: VR to PS
|  | Inbound Dashboard Mock Up (Phase 1) | PGGISVISTA-28 | Inbound Dashboard for the Operations Team. | bar: VR to PS
|  | Inbound Phase 2 | PGGISVISTA-35 | Inbound Phase 2 | bar: VR to PS
|  | Reporting (Tableau) environment setup | PGGISVISTA-53 | Create Reporting (Tableau) environment for GEC. | bar: JP
Vista Phase 2
Vista Phase 3
| Campaign Management | [22 empty] | IS
Unica/Neoline | bar: NS
Functional requirements/Demo | bar: NS
System Recommendations | bar: NS
Integration Layer Development for Inbound/Outbound | bar: NS
System QA | bar: NS
System UAT | bar: NS
Pilot POC | bar: NS
| BI Reporting | [22 empty] | IS
|  |  | USCBIREP-149 | Netezza Upgrade | bar: SS to SK
|  |  | USCBIREP-150 | Golden Gate Upgrade | bar: SS to SK
|  |  | USCBIREP-153 | 13.5- Site to Store Locker | bar: SS to SK
|  |  | USCBIREP-145 | 13.5- MDE Enhancements for Project Mercury - SLA Ranking | bar: SS to SM
|  |  | USCBIREP-154 | 13.5 - MDE Enhancements for Project Mercury - Capacity | bar: SS to SK
|  |  | USCBIREP-25 | 13.5- PUT Reshop via S2S | bar: SS to SK
|  |  | USCBIREP-72 | 13.7-Simplified Shipping Project | bar: SS to SK
13.9-Project Layaway | bar: SS to SK
| KPI Glass | [22 empty] | AS
Finance metrics and scorecards | bar: LS; SM
| CRM | [22 empty] | IS
Greenplum Upgrade | bar: DS
IDelta sync up | bar: DS
Pangaea - Cust and Cart | bar: DS
DFM enhancement | bar: DS
Shelf Impression Analysis Project | bar: DS
| Site Analytics for .com | [22 empty] | IS
Tracking submitted estimated calculated shipping and tax info on Thank you page
Track creating an account, and registering an email address for notifications
Provide marketing classification data for 3 new variables captured in the Adobe (Omniture SiteCatalyst) website tracking reporting.
Ongoing Site Projects
| Marketing | [22 empty] | AS
Automation of datafeeds used for FB marketing
| HR Tableau | [22 empty] | AS
HR needs Tableau reports to provide visualization on current and prospective employee data. | bar: LS
Cart
<TBD>
Payments
<TBD>
Shipping
<TBD>
Customer Interaction
<TBD>
Finance
Waterfall Project
EMC
Electronic Multi Channel Integration
Fraud
<TBD>
Registry
<TBD>
Metadata Repository
Implementation of metdata repository
Data Integration with DW
<TBD>

## Sheet1 (hidden)
Item Dimension | IMS
Product Dimension | IMS
Phase 1 and 2 SC reports | IMS
CS Phase 2 | CS
Fraud
Registry
Implementation of metadata repository
Scalability tuneup for marketplace | Environment